## Guide
BI Migration Estimator v2
Quotable fixed-price estimate for BI report and semantic-model migrations.
How to use
| 1. Setup | Enter engagement details, iteration length, team and ramp settings, SIT/UAT/deployment cadence, automation % by phase and cost mode.
| 2. Scope | One row per migration pair. Pick or type the source and target BI tool and data platform, then inventory, complexity mix, rationalisation, semantic models, security and AI readiness. Example rows are provided - overwrite them.
| 3. Risks | List named risks with impact hours and probability. Expected hours become the risk reserve.
| 4. Roles | Choose the rate-card row for each plan role and adjust the role mix per phase (each row totals 100%).
| 5. Checks | Fix every FAIL. The Summary banner turns green only when all checks pass.
| 6. Summary | Read the price, effort, duration, team and dates. Print Summary and Assumptions for the proposal.
| 7. Plan | Review the weekly headcount. Use the manual adjustment rows to reshape the team; the reconciliation check flags gaps over the tolerance.
Colour key
| Input | Yellow cell with blue text: editable input (all other cells are locked; sheets are protected without a password).
| Calculated | Black text: formula - do not overwrite.
| Header | Table header.
Tabs
| Summary | One-page quotable view.
| Setup | Engagement-wide inputs.
| Scope | Migration pairs (up to 20).
| Risks | Risk register.
| Roles | Plan roles, rate selection and role mix by phase.
| Rates | Rate card (bill rates, USD/h).
| Lists | Tools, archetypes, known pair factors, data platforms.
| Baseline | Reference values with status: Carried / Reshaped / New proposal / User decision.
| Effort | Hours per pair and phase; programme-level hours; totals.
| Schedule | Iterations, waves, phase windows, milestones.
| Plan | Weekly hours and headcount by role.
| Cost | Cost by role and phase; price build-up; payment milestones.
| Assumptions | Printable assumptions and exclusions.
| Checks | Validation; must all PASS.
| Scenarios | Side-by-side comparison of saved options.
| ChangeLog | Version history.
Method
Report development = full-effort pages x mix-weighted hours per page x pair factor x data-platform uplift x report-type factor x (1 - learning gain) x (1 - automation saving), plus derived and merge hours.
Semantic models = target models x mix-weighted model hours x approach share x pair factor x platform uplift, plus consolidation hours, less automation saving.
Iterations: report hours / (peak team x hours per week) plus half the ramp weeks, divided by iteration length (or fixed directly).
SIT runs one iteration behind development and UAT two behind; both are sized per iteration (crew x weeks), plus a final regression and UAT cycle.
Automation saving per phase = automation % x automatable cap, so automation never removes the review and validation work.
No step tiers: initiation and analysis interpolate between the old calculator's tier values.

## Summary
BI Migration Estimate - Example Client
BI modernisation programme ¦ v2.0-draft ¦ 13-Oct-2026 ¦ Start 04-Jan-2027 ¦ All money in USD
VALID ESTIMATE - all checks pass
Fixed price |  | Total effort (hours) |  |  | Duration (working weeks) |  | Planned end date
1069220.9198 |  | 17010.7631 |  |  | 36 |  | 2027-09-24
Development iterations |  | Releases |  |  | Peak team (FTE) |  | Average team (FTE)
10 x 2 wk |  | 2 |  |  | 18.5 |  | 9.8194
Average team during report iterations: 14.4 FTE ¦ Contingency 18.1% ¦ Onsite share 1.2% ¦ Cost mode: Role mix
Effort and cost by phase |  |  |  |  | Team and cost by role
Phase | Hours | % of hours | Cost (USD) | Weeks (start-end) | Role | Location | Hours | Rate (USD/h) | Cost (USD)
Initiation & assessment | 693 | 4.838% | 67983.3 | 1 - 6 | Delivery manager / PM | India | 1440 | 82 | 118080
Architecture & design | 128 | 0.8936% | 13510.4 | 4 - 5 | Onsite architect | USA | 170.6 | 185 | 31561
Semantic model build & consolidation | 2377.94 | 16.6% | 147432.28 | 7 - 18 | Solution architect | India | 259.1 | 87 | 22541.7
Report development & unit validation | 6206.6629 | 43.33% | 345090.4571 | 9 - 28 | BI architect | India | 765.891 | 70 | 53612.37
SIT & optimization | 1840 | 12.85% | 105340 | 11 - 31 | Lead | India | 1693.2573 | 70 | 118528.0103
UAT support | 440 | 3.072% | 25872 | 13 - 34 | Sr. engineer | India | 3884.1689 | 62 | 240818.4699
Deployment support | 400 | 2.792% | 25760 | 13 - 34 | Engineer | India | 4823.5857 | 50 | 241179.2869
Hypercare | 320 | 2.234% | 19520 | 27 - 36 | QA engineer | India | 1288 | 57.5 | 74060
Security, operations & handover | 351 | 2.45% | 23446.8 | 9 - 34 | Total |  | 14324.6029 |  | 900380.8371
AI readiness | 128 | 0.8936% | 8345.6 | 9 - 28
Project management | 1440 | 10.05% | 118080 | 1 - 36
Base effort | 14324.6029 |  | 900380.8371 |  | Key dates
Contingency | 2596.1602 |  | 163183.083 |  | Milestone | Week | Date
Risk reserve | 90 |  | 5656.9998 |  | Assessment sign-off | 6 | 2027-02-19
Discount |  |  | 0 |  | Architecture sign-off | 5 | 2027-02-12
Pass-throughs |  |  | 0 |  | First semantic models ready | 8 | 2027-03-05
FIXED PRICE | 17010.7631 |  | 1069220.9198 |  | First report iteration starts | 9 | 2027-03-12
[5 empty] | Last report iteration ends | 28 | 2027-07-30
[5 empty] | Wave 1 go-live | 26 | 2027-07-16
[5 empty] | Wave 2 go-live | 34 | 2027-09-10
Effort by migration pair |  |  |  |  | Wave 3 go-live
Pair | Source -> target | Reports to build | Hours (incl. shared) | Contingency % | Wave 4 go-live
Finance OBIEE to Power BI | OBIEE -> Power BI | 280 | 9849.9056 | 15% | Wave 5 go-live
Sales Tableau to Power BI | Tableau -> Power BI | 175 | 4474.6973 | 25% | Hypercare exit / programme end | 36 | 2027-09-24

## Setup
Setup
Engagement-wide settings. Yellow cells are inputs; hover a cell for guidance.
Engagement
| Client | Example Client
| Opportunity | BI modernisation programme
| Estimate version | v2.0-draft
Prepared by
| Estimate date | 2026-10-13
| Currency | USD
| Planned start date (Monday) | 2027-01-04
Delivery parameters
| Iteration length (weeks) | 2
| Productive hours per person-week | 40
| Holiday allowance (stretches calendar dates only) | 4%
| Engagement type | Pure BI
| Solve mode | Fix team, compute iterations
| Peak report-development team (FTE) - used when fixing team | 10
| Development iterations - used when fixing iterations | 8
| Ramp-up weeks (report development) | 3
| Ramp-down weeks (report development) | 3
| Assessment team (FTE) | 3
| Architecture team (FTE) | 2
| Architecture overlap with assessment | 50%
| Model lead time before report iterations (weeks) | 2
| Headcount rounding step (0 = no rounding) | 0.5
| PM FTE (pure BI engagements) | 1
SIT, UAT and deployment support (sized per development iteration)
| SIT weeks per iteration | 1
| SIT minimum engineers | 1
| SIT crew sizing (% of dev hours per iteration) | 15%
| SIT fixed hours per iteration (environments, regression) | 8
| Final regression cycle (weeks) | 1
| UAT support weeks per iteration | 1
| UAT engineers when volume <= threshold | 1
| UAT engineers when volume > threshold | 2
| Volume threshold (report pages per iteration) | 150
| Final UAT cycle (weeks) | 1
| Deployment support weeks per iteration | 1
| Deployment support engineers | 1
| Deployment pipeline available? | Yes
| Hypercare weeks per go-live | 2
| Hypercare crew (FTE) | 2
Automation by phase (global; pairs may override assessment, semantic and report automation on Scope)
| Phase | Automation % | Automatable cap | Effective saving
| Assessment | 0% | 60% | 0%
| Semantic model | 0% | 40% | 0%
| Report development | 0% | 60% | 0%
| SIT | 0% | 30% | 0%
| UAT support | 0% | 20% | 0%
| Deployment support | 0% | 60% | 0%
Cost
| Cost mode | Role mix
| Blended rate (USD/h) - used in Blended mode | 60
| Discount on bill rates | 0%
| Pass-through: tools / licences (USD) | 0
| Pass-through: travel (USD) | 0
| Pass-through: other (USD) | 0
Payment milestones (must total 100%)
| Contract signature | 10%
| Assessment sign-off | 15%
| Architecture sign-off | 10%
| Mid-development | 25%
| Final go-live | 30%
| Hypercare exit | 10%
| Total | 100%
Note on C14: Development iteration = SIT/UAT cadence. 1 or 2 weeks.
Note on C15: User decision: 40 productive hours (of 42.5 worked).
Note on C17: Bundled = PM carried by the ETL/EDW programme, so PM hours are 0.
Note on C26: Old calculator B13 - now used.
Note on C33: Old calculator B14 (15%) now sizes the per-iteration SIT crew.
Note on C41: Usually less than the UAT support cycle.
Note on C43: No = add manual deployment hours per report.

## Scope
Scope
One row per migration pair (source BI tool + data platform -> target BI tool + data platform). Rows with a source, target and report count are active.
Mixes are fractions that total 100% per row. Retired + Consolidated <= 100%; Derived applies to what remains. Blank automation override = use Setup.
Pair | [6 empty] | Report inventory |  |  |  | Report complexity |  |  |  | Rationalisation |  |  | Semantic layer | [5 empty] | Security, ops, AI |  |  |  | Overrides and confidence
# | Pair name | Source BI tool | Target BI tool | Source data platform | Target data platform | Release wave (1-5) | Reports in inventory | Avg pages (sheets) per report | % paginated | % with custom SQL | % Simple | % Medium | % Complex | % Very Complex | % Retired | % Consolidated | % Derived | Source semantic models / SQL datasets | Model % Simple | Model % Medium | Model % Complex | Model % Very Complex | Target semantic models | Security model | Schedules / subscriptions / alerts | User groups | AI readiness | Pair factor override | Override reason | Automation override - Assessment | Automation override - Semantic | Automation override - Reports | Input confidence | Notes
1 | Finance OBIEE to Power BI | OBIEE | Power BI | Oracle | Snowflake | 1 | 400 | 3 | 10% | 15% | 40% | 35% | 20% | 5% | 20% | 10% | 10% | 12 | 30% | 40% | 20% | 10% | 8 | Row-level | 150 | 20 | Basic | [5 empty] | Customer inventory | Example row - replace with real scope
2 | Sales Tableau to Power BI | Tableau | Power BI | Amazon Redshift | Snowflake | 2 | 250 | 2 | 0% | 10% | 50% | 30% | 15% | 5% | 25% | 5% | 10% | 40 | 50% | 30% | 15% | 5% | 10 | Role-based | 60 | 10 | None | [5 empty] | Verbal estimate | Example row - replace with real scope
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Risks
Risks
Named risks priced at expected value (impact hours x probability). Example rows - replace with the engagement's risks.
# | Risk | Impact (hours) | Probability | Expected hours | Owner | Mitigation
1 | Target data platform tables not ready when report iterations start | 200 | 30% | 60 | Customer | Model-lead gate; mock data for unit tests
2 | Custom visuals / extensions with no target equivalent | 120 | 25% | 30 | BI lead | Identify in assessment; agree alternatives
3 |  |  |  | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0
|  |  | Total | 90

## Roles
Roles
Plan roles (each priced from one rate-card row) and the share of each phase's hours carried by each role.
Plan roles
# | Plan role | Rate-card key (Role ¦ Grade ¦ Location) | Rate (USD/h) | Location
1 | Delivery manager / PM | MSE I ¦ G12 ¦ India | 82 | India
2 | Onsite architect | Architect II ¦ G12 ¦ USA | 185 | USA
3 | Solution architect | Sr. Architect I ¦ G13 ¦ India | 87 | India
4 | BI architect | Architect II ¦ G11 ¦ India | 70 | India
5 | Lead | Lead II ¦ G11 ¦ India | 70 | India
6 | Sr. engineer | Sr. Engineer II ¦ G10 ¦ India | 62 | India
7 | Engineer | Engineer II ¦ G8 ¦ India | 50 | India
8 | QA engineer | Sr. Engineer I ¦ G9 ¦ India | 57.5 | India
Role mix by phase (share of phase hours; each row must total 100%)
# | Phase | Delivery manager / PM | Onsite architect | Solution architect | BI architect | Lead | Sr. engineer | Engineer | QA engineer | Total
1 | Initiation & assessment | 0% | 20% | 30% | 30% | 20% | 0% | 0% | 0% | 100%
2 | Architecture & design | 0% | 25% | 40% | 35% | 0% | 0% | 0% | 0% | 100%
3 | Semantic model build & consolidation | 0% | 0% | 0% | 15% | 15% | 50% | 20% | 0% | 100%
4 | Report development & unit validation | 0% | 0% | 0% | 0% | 10% | 30% | 60% | 0% | 100%
5 | SIT & optimization | 0% | 0% | 0% | 0% | 10% | 0% | 20% | 70% | 100%
6 | UAT support | 0% | 0% | 0% | 0% | 20% | 40% | 40% | 0% | 100%
7 | Deployment support | 0% | 0% | 0% | 0% | 30% | 70% | 0% | 0% | 100%
8 | Hypercare | 0% | 0% | 0% | 0% | 25% | 50% | 25% | 0% | 100%
9 | Security, operations & handover | 0% | 0% | 0% | 30% | 30% | 40% | 0% | 0% | 100%
10 | AI readiness | 0% | 0% | 0% | 40% | 0% | 60% | 0% | 0% | 100%
11 | Project management | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%

## Rates
Rates
Rate card (bill rates, USD per hour) as provided. Key = Role ¦ Grade ¦ Location is what the Roles tab selects.
Role | Grade | Location | Rate (USD/h) | Key | Notes
MSE II | G13 | India | 87 | MSE II ¦ G13 ¦ India | Source: rate card supplied by the user (bill rates, USD/h). Lead I rows added from the requirements review. MSE = Manager Software Engineer.
MSE I | G12 | India | 82 | MSE I ¦ G12 ¦ India
Architect II | G12 | India | 70 | Architect II ¦ G12 ¦ India
Architect I | G11 | India | 65 | Architect I ¦ G11 ¦ India
Lead II | G11 | India | 70 | Lead II ¦ G11 ¦ India
Lead II | G10 | India | 70 | Lead II ¦ G10 ¦ India
Lead I | G10 | India | 62 | Lead I ¦ G10 ¦ India
Lead I | G9 | India | 62 | Lead I ¦ G9 ¦ India
Sr. Engineer II | G10 | India | 62 | Sr. Engineer II ¦ G10 ¦ India
Sr. Engineer II | G9 | India | 62 | Sr. Engineer II ¦ G9 ¦ India
Sr. Engineer I | G9 | India | 57.5 | Sr. Engineer I ¦ G9 ¦ India
Sr. Engineer I | G8 | India | 57.5 | Sr. Engineer I ¦ G8 ¦ India
Engineer II | G8 | India | 50 | Engineer II ¦ G8 ¦ India
Engineer II | G6 | India | 50 | Engineer II ¦ G6 ¦ India
Engineer I | G6 | India | 42 | Engineer I ¦ G6 ¦ India
Engineer I | G4 | India | 42 | Engineer I ¦ G4 ¦ India
Jr. Engineer | G4 | India | 35 | Jr. Engineer ¦ G4 ¦ India
Architect II | G11 | India | 70 | Architect II ¦ G11 ¦ India
Sr. Architect I | G13 | India | 87 | Sr. Architect I ¦ G13 ¦ India
Sr. Architect II | G14 | India | 105 | Sr. Architect II ¦ G14 ¦ India
Sr. Architect II | G13 | India | 105 | Sr. Architect II ¦ G13 ¦ India
Architect II | G12 | USA | 185 | Architect II ¦ G12 ¦ USA
MSE I | G12 | USA | 190 | MSE I ¦ G12 ¦ USA
MSE II | G13 | USA | 210 | MSE II ¦ G13 ¦ USA

## Lists
Lists
Reference lists behind the drop-downs. BI team maintains; add rows in the blank space - no formula changes needed.
BI tools and archetypes |  | Archetypes | Pair factor fallback by archetype (source row x target column) - proposal, BI team to confirm |  |  |  |  | Known pair factors (seeded from old calculator BD7:BD21) |  |  |  | Data platforms
BI tool | Archetype | Archetype | Source \ Target | Enterprise semantic-layer | Paginated / pixel-perfect | Modern visual / self-service | Modern code-based semantic | Source BI tool | Target BI tool | Factor | Key | Data platform | YesNo | EngTypes | SolveModes | CostModes | IterLens
SAP BusinessObjects | Enterprise semantic-layer | Enterprise semantic-layer | Enterprise semantic-layer | 1.1 | 1 | 1.1 | 1.2 | OBIEE | Power BI | 1 | OBIEE¦Power BI | Oracle | Yes | Pure BI | Fix team, compute iterations | Role mix | 1
OBIEE | Enterprise semantic-layer | Paginated / pixel-perfect | Paginated / pixel-perfect | 1 | 0.9 | 1.05 | 1.2 | Cognos | Power BI | 1.1 | Cognos¦Power BI | SQL Server | No | Bundled with ETL/EDW programme | Fix iterations, compute team | Blended | 2
Oracle Analytics Server | Enterprise semantic-layer | Modern visual / self-service | Modern visual / self-service | 1.1 | 1 | 0.95 | 1.1 | SAP BusinessObjects | Power BI | 1.25 | SAP BusinessObjects¦Power BI | Teradata
MicroStrategy | Enterprise semantic-layer | Modern code-based semantic | Modern code-based semantic | 1 | 1 | 1 | 1 | Tableau | Power BI | 0.95 | Tableau¦Power BI | Netezza
Cognos | Enterprise semantic-layer | [6 empty] | SSRS | Power BI | 1.05 | SSRS¦Power BI | DB2
SSRS | Paginated / pixel-perfect | [6 empty] | OBIEE | QuickSight | 1.2 | OBIEE¦QuickSight | SAP HANA
Crystal Reports | Paginated / pixel-perfect |  | Semantic-model approach by archetype (source row x target column) |  |  |  |  | Cognos | QuickSight | 1.25 | Cognos¦QuickSight | Snowflake
Tableau | Modern visual / self-service |  | Source \ Target | Enterprise semantic-layer | Paginated / pixel-perfect | Modern visual / self-service | Modern code-based semantic | Tableau | QuickSight | 1.1 | Tableau¦QuickSight | Databricks
Power BI | Modern visual / self-service |  | Enterprise semantic-layer | Redesign | Redesign | Redesign | Author (LookML) | SSRS | QuickSight | 1.2 | SSRS¦QuickSight | Google BigQuery
QuickSight | Modern visual / self-service |  | Paginated / pixel-perfect | Shared datasets | Shared datasets | Shared datasets | Author (LookML) | SAP BusinessObjects | QuickSight | 1.3 | SAP BusinessObjects¦QuickSight | Amazon Redshift
Qlik Sense | Modern visual / self-service |  | Modern visual / self-service | Redesign | Shared datasets | Translate | Author (LookML) | Cognos | Looker | 1.25 | Cognos¦Looker | Azure Synapse
QlikView | Modern visual / self-service |  | Modern code-based semantic | Translate | Shared datasets | Translate | Translate | OBIEE | Looker | 1.2 | OBIEE¦Looker | Microsoft Fabric
Looker Studio | Modern visual / self-service | [6 empty] | Tableau | Looker | 1.1 | Tableau¦Looker | PostgreSQL
Looker | Modern code-based semantic | [6 empty] | SSRS | Looker | 1.2 | SSRS¦Looker | Other
[8 empty] | SAP BusinessObjects | Looker | 1.3 | SAP BusinessObjects¦Looker

## Baseline
Baseline
Reference values used by the engine. Status shows where each value came from. Change values here only with BI-team sign-off.
Parameter | Value | Unit | Status | Source / note
Report development
Hours per report page - Simple | 3.625 | h / page | Carried | Old calculator F5
Hours per report page - Medium | 6.625 | h / page | Carried | Old calculator F6
Hours per report page - Complex | 9.125 | h / page | Carried | Old calculator F7
Hours per report page - Very Complex | 12.625 | h / page | Carried | Old calculator F8
Hours per derived (similar) report page | 1 | h / page | Carried | Old calculator F9
Learning gain - quarter 1 of iterations | 0% | % saving | Reshaped | User decision 0/10/15/20% (old file 0/15/20/25% by page-tier phase). Applied by quarter of the iteration run.
Learning gain - quarter 2 of iterations | 10% | % saving | Reshaped | User decision 0/10/15/20% (old file 0/15/20/25% by page-tier phase). Applied by quarter of the iteration run.
Learning gain - quarter 3 of iterations | 15% | % saving | Reshaped | User decision 0/10/15/20% (old file 0/15/20/25% by page-tier phase). Applied by quarter of the iteration run.
Learning gain - quarter 4 of iterations | 20% | % saving | Reshaped | User decision 0/10/15/20% (old file 0/15/20/25% by page-tier phase). Applied by quarter of the iteration run.
Average learning gain (effort is spread evenly over iterations) | 11.25% |  | Calculated
Paginated report effort factor | 1.2 | x | New proposal | Paginated / pixel-perfect pages vs interactive pages
Data-platform change uplift on custom-SQL reports | 25% | % uplift | New proposal | Applied to the custom-SQL share when source and target data platforms differ
Merge hours per consolidated report | 2 | h / report | New proposal | Effort to fold a consolidated report into the report that absorbs it
Semantic models
Model build hours - Simple | 80 | h / model | New proposal | Replaces old 16/40/80 by reports-per-model (E16); SOP minimum 80 h
Model build hours - Medium | 120 | h / model | New proposal | Replaces old 16/40/80 by reports-per-model (E16); SOP minimum 80 h
Model build hours - Complex | 200 | h / model | New proposal | Replaces old 16/40/80 by reports-per-model (E16); SOP minimum 80 h
Model build hours - Very Complex | 320 | h / model | New proposal | Replaces old 16/40/80 by reports-per-model (E16); SOP minimum 80 h
Consolidation hours per source model merged | 16 | h / model | New proposal | Applied to (source models - target models)
Data-platform change uplift on semantic models | 15% | % uplift | New proposal | When source and target data platforms differ
Redesign | 100% | share of build h | New proposal | Semantic-model approach share of full build hours
Translate | 40% | share of build h | New proposal | Semantic-model approach share of full build hours
Author (LookML) | 100% | share of build h | New proposal | Semantic-model approach share of full build hours
Shared datasets | 30% | share of build h | New proposal | Semantic-model approach share of full build hours
Initiation and assessment (interpolation anchors on inventory pages)
Anchor | Pages | Initiation h | Analysis h | Source
Anchor 1 | 100 | 40 | 80 | Reshaped: old tier values E14/E15 become straight-line anchors (no cliffs)
Anchor 2 | 500 | 60 | 160 | Reshaped: old tier values E14/E15 become straight-line anchors (no cliffs)
Anchor 3 | 1000 | 80 | 240 | Reshaped: old tier values E14/E15 become straight-line anchors (no cliffs)
Anchor 4 | 5000 | 120 | 360 | Reshaped: old tier values E14/E15 become straight-line anchors (no cliffs)
Anchor 5 | 10000 | 160 | 480 | Reshaped: old tier values E14/E15 become straight-line anchors (no cliffs)
Assessment hours per source semantic model | 4 | h / model | New proposal | Inventorying universes / RPD subject areas / packages / SQL datasets
Architecture, security, operations, AI readiness
Architecture hours per distinct target BI tool | 80 | h / tool | New proposal | Tenant/workspace design, security, connectivity, CI/CD, performance, standards
Architecture hours per migration pair | 24 | h / pair | New proposal | Pair-specific design decisions
None | 0 | h / target model | New proposal | Security model build and testing per target semantic model
Role-based | 4 | h / target model | New proposal | Security model build and testing per target semantic model
Row-level | 12 | h / target model | New proposal | Security model build and testing per target semantic model
Row + object-level | 20 | h / target model | New proposal | Security model build and testing per target semantic model
Hours per schedule / subscription / alert | 0.5 | h / item | New proposal | Recreate in target
Hours per user group | 1 | h / group | New proposal | Groups, workspace access
Training and handover per pair | 40 | h / pair | New proposal | Demo, documentation, knowledge transfer
None | 0 | h / target model | Placeholder | AI readiness (descriptions, synonyms, Copilot / Q&A / Amazon Q / Gemini set-up). No baseline yet - BI team to set.
Basic | 16 | h / target model | Placeholder | AI readiness (descriptions, synonyms, Copilot / Q&A / Amazon Q / Gemini set-up). No baseline yet - BI team to set.
Advanced | 40 | h / target model | Placeholder | AI readiness (descriptions, synonyms, Copilot / Q&A / Amazon Q / Gemini set-up). No baseline yet - BI team to set.
Automation and deployment
Automatable share cap - Assessment | 60% | % of phase | User decision | Max share of the phase automation can remove (requirements Q6)
Automatable share cap - Semantic model | 40% | % of phase | User decision | Max share of the phase automation can remove (requirements Q6)
Automatable share cap - Report development | 60% | % of phase | User decision | Max share of the phase automation can remove (requirements Q6)
Automatable share cap - SIT | 30% | % of phase | User decision | Max share of the phase automation can remove (requirements Q6)
Automatable share cap - UAT support | 20% | % of phase | User decision | Max share of the phase automation can remove (requirements Q6)
Automatable share cap - Deployment support | 60% | % of phase | User decision | Max share of the phase automation can remove (requirements Q6)
Automation tool set-up per pair (when any automation > 0) | 40 | h / pair | New proposal | Accelerator configuration and runs
Manual deployment hours per report (no pipeline) | 0.5 | h / report | Carried | Old calculator E20
Contingency and controls
Tool-assessed | 10% | contingency | New proposal | Replaces old flat 15% (B39). Driven by each pair's input confidence.
Customer inventory | 15% | contingency | New proposal | Replaces old flat 15% (B39). Driven by each pair's input confidence.
Verbal estimate | 25% | contingency | New proposal | Replaces old flat 15% (B39). Driven by each pair's input confidence.
Pair factor override - minimum | 0.7 | x | New proposal | Overrides are clamped to this range
Pair factor override - maximum | 2 | x | New proposal
Plan reconciliation tolerance | 5% | +/- % | New proposal | Plan hours vs estimate hours

## Effort
Effort
Hours per pair and per phase. Locked - every value is calculated from Scope, Setup and Baseline.
# | Pair | Active | Source archetype | Target archetype | Suggested pair factor | Pair factor used | Semantic approach | Approach share | Data platform change | Report platform uplift | Model platform uplift | Report-type factor | Saving - assessment | Saving - semantic | Saving - reports | Inventory pages | Reports to build | Derived reports | Full-effort reports | Full-effort pages | Derived pages | Consolidated reports | Mix-weighted h / page | Report base hours | Merge hours | REPORT DEVELOPMENT h | Target models | Mix-weighted h / model | Model build hours | Consolidation hours | SEMANTIC MODEL h | ASSESSMENT (analysis) h | SECURITY, OPS & HANDOVER h | AI READINESS h | Automation set-up h | Pair direct hours | Development hours (semantic + reports) | Wave | Contingency % | Allocated programme hours | PAIR TOTAL h (before contingency) | Contingency h | Flag: mix not 100% | Flag: rationalisation > 100% | Flag: unmapped tool | Flag: override without reason | Flag: pages < 1 or no target model
1 | Finance OBIEE to Power BI | 1 | Enterprise semantic-layer | Modern visual / self-service | 1 | 1 | Redesign | 100% | 1 | 1.0375 | 1.15 | 1.02 | 0% | 0% | 0% | 1200 | 280 | 28 | 252 | 756 | 84 | 40 | 6.225 | 5064.2303 | 80 | 4574.5044 | 8 | 144 | 1324.8 | 64 | 1388.8 | 294 | 231 | 128 | 0 | 6616.3044 | 5963.3044 | 1 | 15% | 3233.6012 | 9849.9056 | 1477.4858 | 0 | 0 | 0 | 0 | 0
2 | Sales Tableau to Power BI | 1 | Modern visual / self-service | Modern visual / self-service | 0.95 | 0.95 | Translate | 40% | 1 | 1.025 | 1.15 | 1 | 0% | 0% | 0% | 500 | 175 | 17.5 | 157.5 | 315 | 35 | 12.5 | 5.8 | 1812.2912 | 23.75 | 1632.1585 | 10 | 122 | 533.14 | 456 | 989.14 | 312 | 120 | 0 | 0 | 3053.2985 | 2621.2985 | 2 | 25% | 1421.3988 | 4474.6973 | 1118.6743 | 0 | 0 | 0 | 0 | 0
3 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | 0 |  |  | 0 | 0 |  | 0% | 0 | 1 | 1 | 1 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 2 | [13 empty] | 1700 | 455 | 45.5 |  | 1071 | 119 | 52.5 |  |  |  | 6206.6629 | 18 |  |  |  | 2377.94 | 606 | 351 | 128 | 0 | 9669.6029 | 8584.6029 |  |  | 4655 | 14324.6029 | 2596.1602 | 0 | 0 | 0 | 0 | 0
Programme-level effort (shared across pairs)
| Item | Hours | Basis
| Initiation (programme) | 87 | Interpolated on total inventory pages; old E14 anchors
| Distinct target BI tools | 1 | Count
| Architecture & design | 128 | Per target tool + per pair
| SIT & optimization | 1840 | Per iteration crew x weeks + fixed + final regression
| UAT support | 440 | Per iteration: 1-2 engineers x 1-2 weeks by volume
| Deployment support | 400 | Per iteration, plus manual deployment without a pipeline
| Hypercare | 320 | Per go-live
| Project management | 1440 | PM FTE x duration; 0 when bundled
| Shared hours allocated to pairs by development hours | 4655
Hours by phase
# | Phase | Hours | % of total
1 | Initiation & assessment | 693 | 4.838%
2 | Architecture & design | 128 | 0.8936%
3 | Semantic model build & consolidation | 2377.94 | 16.6%
4 | Report development & unit validation | 6206.6629 | 43.33%
5 | SIT & optimization | 1840 | 12.85%
6 | UAT support | 440 | 3.072%
7 | Deployment support | 400 | 2.792%
8 | Hypercare | 320 | 2.234%
9 | Security, operations & handover | 351 | 2.45%
10 | AI readiness | 128 | 0.8936%
11 | Project management | 1440 | 10.05%
| Total base hours | 14324.6029
| Contingency % (weighted by pair input confidence) | 18.12%
| Contingency hours | 2596.1602
| Risk reserve hours (Risks tab) | 90
| TOTAL HOURS incl. contingency and risk | 17010.7631

## Schedule
Schedule
Iterations, windows and milestones (working weeks from the planned start). Locked.
Development iterations
| Assessment weeks | 6
| Assessment end week | 6
| Architecture start week | 4
| Architecture end week | 5
| Development start week (semantic models) | 7
| First report iteration starts (week) | 9
| Development iterations | 10
| Report development weeks | 20
| Last report iteration ends (week) | 28
| Semantic model build ends (week) | 18
| Peak report-development team (FTE, before rounding) | 9.1274
| Development hours per iteration | 858.4603
| Report pages delivered per iteration | 119
| SIT engineers per iteration | 4
| UAT support engineers per iteration | 1
| SIT window starts (one iteration behind) | 11
| SIT window ends (incl. final regression) | 31
| UAT window starts (two iterations behind) | 13
| Final go-live week | 34
Release waves
| Wave | Development hours | Cumulative hours | Cumulative iterations | Has scope (wave no.) | Go-live week
| 1 | 5963.3044 | 5963.3044 | 7 | 1 | 26
| 2 | 2621.2985 | 8584.6029 | 10 | 2 | 34
| 3 | 0 | 8584.6029 | 10 | 0
| 4 | 0 | 8584.6029 | 10 | 0
| 5 | 0 | 8584.6029 | 10 | 0
| Last wave with scope | 2
| Releases (go-lives) | 2
| First go-live week | 26
| Hypercare starts (week) | 27
| Programme end week (last go-live + hypercare) | 36
| DURATION (working weeks) | 36
| Duration in calendar weeks (incl. holiday allowance) | 38
| Planned end date | 2027-09-24
Phase windows (feed the weekly Plan)
| Phase | Start week | End week | Profile | Hours | Weeks
| Initiation & assessment | 1 | 6 | Flat | 693 | 6
| Architecture & design | 4 | 5 | Flat | 128 | 2
| Semantic model build & consolidation | 7 | 18 | Flat | 2377.94 | 12
| Report development & unit validation | 9 | 28 | Ramp | 6206.6629 | 20
| SIT & optimization | 11 | 31 | Flat | 1840 | 21
| UAT support | 13 | 34 | Flat | 440 | 22
| Deployment support | 13 | 34 | Flat | 400 | 22
| Hypercare | 27 | 36 | Flat | 320 | 10
| Security, operations & handover | 9 | 34 | Flat | 351 | 26
| AI readiness | 9 | 28 | Flat | 128 | 20
| Project management | 1 | 36 | Flat | 1440 | 36
Milestones
| Milestone | Week | Date (end of week)
| Assessment sign-off | 6 | 2027-02-19
| Architecture sign-off | 5 | 2027-02-12
| First semantic models ready | 8 | 2027-03-05
| First report iteration starts | 9 | 2027-03-12
| Last report iteration ends | 28 | 2027-07-30
| Wave 1 go-live | 26 | 2027-07-16
| Wave 2 go-live | 34 | 2027-09-10
Wave 3 go-live
Wave 4 go-live
Wave 5 go-live
| Hypercare exit / programme end | 36 | 2027-09-24
Formulas:
Cumulative hours = IF(ISNUMBER([Development hours]),StartDate+ROUNDUP([Development hours]*(1+HolidayPct),0)*7-3,"")

## Plan
Plan
Weekly resource loading for up to 104 working weeks. Phase hours are spread over their windows; report development ramps up, peaks and ramps down.
Row | Start wk | End wk | Hours | Profile / label
Working week |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104
Week starting | time axis 2027-01-04 to 2028-12-25
Phase hours per week
Initiation & assessment | 1 | 6 | 693 | Flat | 115.5 | 115.5 | 115.5 | 115.5 | 115.5 | 115.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Architecture & design | 4 | 5 | 128 | Flat | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Semantic model build & consolidation | 7 | 18 | 2377.94 | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 198.1617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Report development & unit validation | 9 | 28 | 6206.6629 | Ramp | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.2745 | 182.5489 | 273.8234 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 365.0978 | 273.8234 | 182.5489 | 91.2745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SIT & optimization | 11 | 31 | 1840 | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 87.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT support | 13 | 34 | 440 | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deployment support | 13 | 34 | 400 | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 18.1818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hypercare | 27 | 36 | 320 | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security, operations & handover | 9 | 34 | 351 | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AI readiness | 9 | 28 | 128 | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project management | 1 | 36 | 1440 | Flat | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total phase hours |  |  |  |  | 155.5 | 155.5 | 155.5 | 219.5 | 219.5 | 155.5 | 238.1617 | 238.1617 | 349.3361 | 440.6106 | 619.5041 | 710.7785 | 748.9603 | 748.9603 | 748.9603 | 748.9603 | 748.9603 | 748.9603 | 550.7987 | 550.7987 | 550.7987 | 550.7987 | 550.7987 | 550.7987 | 550.7987 | 459.5242 | 400.2498 | 308.9753 | 211.3009 | 211.3009 | 211.3009 | 123.6818 | 123.6818 | 123.6818 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ramp weight (report development) |  |  | 17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 0.75 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours by role per week
Delivery manager / PM |  |  | 1440 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onsite architect |  |  | 170.6 |  | 23.1 | 23.1 | 23.1 | 39.1 | 39.1 | 23.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution architect |  |  | 259.1 |  | 34.65 | 34.65 | 34.65 | 60.25 | 60.25 | 34.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BI architect |  |  | 765.891 |  | 34.65 | 34.65 | 34.65 | 57.05 | 57.05 | 34.65 | 29.7243 | 29.7243 | 36.3342 | 36.3342 | 36.3342 | 36.3342 | 36.3342 | 36.3342 | 36.3342 | 36.3342 | 36.3342 | 36.3342 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 4.05 | 4.05 | 4.05 | 4.05 | 4.05 | 4.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lead |  |  | 1693.2573 |  | 23.1 | 23.1 | 23.1 | 23.1 | 23.1 | 23.1 | 29.7243 | 29.7243 | 42.9017 | 52.0291 | 69.9185 | 79.0459 | 88.5005 | 88.5005 | 88.5005 | 88.5005 | 88.5005 | 88.5005 | 58.7762 | 58.7762 | 58.7762 | 58.7762 | 58.7762 | 58.7762 | 58.7762 | 49.6488 | 48.5213 | 39.3939 | 30.2665 | 30.2665 | 30.2665 | 21.5045 | 21.5045 | 21.5045 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sr. engineer |  |  | 3884.1689 |  | 0 | 0 | 0 | 0 | 0 | 0 | 99.0808 | 99.0808 | 135.7032 | 163.0855 | 190.4678 | 217.8502 | 238.5775 | 238.5775 | 238.5775 | 238.5775 | 238.5775 | 238.5775 | 139.4966 | 139.4966 | 139.4966 | 139.4966 | 139.4966 | 139.4966 | 139.4966 | 112.1143 | 100.7319 | 73.3496 | 42.1273 | 42.1273 | 42.1273 | 42.1273 | 42.1273 | 42.1273 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer |  |  | 4823.5857 |  | 0 | 0 | 0 | 0 | 0 | 0 | 39.6323 | 39.6323 | 94.397 | 149.1617 | 221.4502 | 276.2148 | 284.2148 | 284.2148 | 284.2148 | 284.2148 | 284.2148 | 284.2148 | 244.5825 | 244.5825 | 244.5825 | 244.5825 | 244.5825 | 244.5825 | 244.5825 | 189.8178 | 143.0532 | 88.2885 | 33.5238 | 33.5238 | 33.5238 | 16 | 16 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA engineer |  |  | 1288 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 61.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computed headcount (FTE)
Delivery manager / PM |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onsite architect |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution architect |  |  |  |  | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BI architect |  |  |  |  | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lead |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sr. engineer |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5 | 3.5 | 4 | 5 | 5.5 | 6 | 6 | 6 | 6 | 6 | 6 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3 | 2.5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2.5 | 3.5 | 5.5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4.5 | 3.5 | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA engineer |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Manual adjustments (+/- FTE) - optional inputs
Delivery manager / PM
Onsite architect
Solution architect
BI architect
Lead
Sr. engineer
Engineer
QA engineer
Final headcount (FTE) - plan of record |  |  | Plan hours
Delivery manager / PM |  |  | 1440 | Delivery manager / PM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onsite architect |  |  | 160 | Onsite architect | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution architect |  |  | 280 | Solution architect | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BI architect |  |  | 720 | BI architect | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lead |  |  | 1600 | Lead | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sr. engineer |  |  | 3920 | Sr. engineer | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5 | 3.5 | 4 | 5 | 5.5 | 6 | 6 | 6 | 6 | 6 | 6 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3 | 2.5 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer |  |  | 4760 | Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2.5 | 3.5 | 5.5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4.5 | 3.5 | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA engineer |  |  | 1260 | QA engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total headcount |  |  | 14140 |  | 4 | 4 | 4 | 5.5 | 5.5 | 4 | 5.5 | 5.5 | 9 | 11 | 15.5 | 18 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 11 | 9.5 | 7.5 | 5.5 | 5.5 | 5.5 | 3 | 3 | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team summary
Peak team (FTE) |  |  | 18.5
Average team over the engagement (FTE) |  |  | 9.8194
Average team during report iterations (FTE) |  |  | 14.35
Total person-weeks |  |  | 353.5
Plan hours vs estimate (variance) |  |  | -1.289%

## Cost
Cost
Cost by role and phase, and the price build-up. Locked.
Cost by role (estimate hours x role mix x rate card)
# | Plan role | Location | Hours | Rate (USD/h) | Cost (USD) | Plan hours
1 | Delivery manager / PM | India | 1440 | 82 | 118080 | 1440
2 | Onsite architect | USA | 170.6 | 185 | 31561 | 160
3 | Solution architect | India | 259.1 | 87 | 22541.7 | 280
4 | BI architect | India | 765.891 | 70 | 53612.37 | 720
5 | Lead | India | 1693.2573 | 70 | 118528.0103 | 1600
6 | Sr. engineer | India | 3884.1689 | 62 | 240818.4699 | 3920
7 | Engineer | India | 4823.5857 | 50 | 241179.2869 | 4760
8 | QA engineer | India | 1288 | 57.5 | 74060 | 1260
| Total |  | 14324.6029 |  | 900380.8371 | 14140
| Implied blended rate from role mix |  |  |  | 62.8556
| Onsite (USA) share of hours |  |  |  | 1.191%
Cost by phase
# | Phase | Hours | Rate used (USD/h) | Cost (USD)
1 | Initiation & assessment | 693 | 98.1 | 67983.3
2 | Architecture & design | 128 | 105.55 | 13510.4
3 | Semantic model build & consolidation | 2377.94 | 62 | 147432.28
4 | Report development & unit validation | 6206.6629 | 55.6 | 345090.4571
5 | SIT & optimization | 1840 | 57.25 | 105340
6 | UAT support | 440 | 58.8 | 25872
7 | Deployment support | 400 | 64.4 | 25760
8 | Hypercare | 320 | 61 | 19520
9 | Security, operations & handover | 351 | 66.8 | 23446.8
10 | AI readiness | 128 | 65.2 | 8345.6
11 | Project management | 1440 | 82 | 118080
| Total | 14324.6029 |  | 900380.8371
Price build-up
| 1. Base cost (selected cost mode) |  |  |  | 900380.8371
| Effective rate (USD/h) |  |  |  | 62.8556
| 2. Contingency (by input confidence) |  |  |  | 163183.083
| 3. Risk reserve (Risks tab) |  |  |  | 5656.9998
| Services before discount |  |  |  | 1069220.9198
| Discount on bill rates |  |  |  | 0
| Services price |  |  |  | 1069220.9198
| 4. Pass-throughs (tools, travel, other) |  |  |  | 0
| 5. FIXED PRICE |  |  |  | 1069220.9198
Payment milestones
# | Milestone | % | Amount (USD)
1 | Contract signature | 10% | 106922.092
2 | Assessment sign-off | 15% | 160383.138
3 | Architecture sign-off | 10% | 106922.092
4 | Mid-development | 25% | 267305.23
5 | Final go-live | 30% | 320766.276
6 | Hypercare exit | 10% | 106922.092

## Assumptions
Assumptions & exclusions
Attach to the proposal. Every value is live from the input and reference tabs.
Engagement
| Client / opportunity | Example Client - BI modernisation programme
| Estimate version and date | v2.0-draft - 13-Oct-2026
| Planned start | 2027-01-04
| Engagement type | Pure BI | Bundled engagements carry PM in the ETL/EDW programme
Delivery assumptions
| Productive hours per person-week | 40
| Iteration length (weeks) | 2
| Development iterations | 10
| Solve mode | Fix team, compute iterations
| Peak report-development team (FTE) | 9.1274
| Ramp-up / ramp-down weeks | 3 / 3
| Model lead time before report iterations (weeks) | 2
| SIT: weeks per iteration / engineers / fixed h per iteration | 1 / 4 / 8
| UAT support: weeks per iteration / engineers | 1 / 1 | 1 engineer up to the volume threshold, 2 above it
| Deployment support: weeks per iteration / engineers | 1 / 1
| Deployment pipeline available | Yes
| Hypercare weeks per go-live / crew | 2 / 2
| Holiday allowance (calendar dates) | 4%
Automation (global % x automatable cap = saving)
| Assessment | 0% x 60% = 0.0%
| Semantic model | 0% x 40% = 0.0%
| Report development | 0% x 60% = 0.0%
| SIT | 0% x 30% = 0.0%
| UAT support | 0% x 20% = 0.0%
| Deployment support | 0% x 60% = 0.0%
Estimation basis
| Hours per report page (S / M / C / VC / Derived) | 3.625 / 6.625 / 9.125 / 12.625 / 1 | Carried from the previous calculator
| Learning gain by quarter of iterations | 0% / 10% / 15% / 20%
| Semantic model hours (S / M / C / VC) | 80 / 120 / 200 / 320
| Contingency (weighted by input confidence) | 18.12%
| Risk reserve hours | 90
| Cost mode / discount | Role mix / 0%
Pair overrides (factor overrides must carry a reason)
| Pair | Suggested -> used factor | Reason
| Finance OBIEE to Power BI | 1.00 -> 1.00
| Sales Tableau to Power BI | 0.95 -> 0.95
Exclusions
Data / ETL / EDW migration and data reconciliation of the underlying platform (estimated separately).
BI and data-platform licences and infrastructure, unless entered as a pass-through.
Remediation of source data quality issues.
Reports retired or consolidated by rationalisation (only merge effort is included).
End-user training beyond the training and handover allowance per pair.
Work outside the scope rows and risk register in this workbook.

## Checks
Checks
Every check must PASS before the estimate is quoted. The Summary banner reads from here.
# | Check | Result | Detail
1 | At least one active migration pair | PASS | 2 active pair(s)
2 | Every active pair maps to source and target archetypes | PASS | 0 pair(s) with an unmapped tool - add the tool on Lists
3 | Report and semantic-model complexity mixes total 100% | PASS | 0 pair(s) with a mix that does not total 100%
4 | Retired + Consolidated <= 100% per pair | PASS | 0 pair(s) over 100%
5 | Every pair-factor override has a reason | PASS | 0 override(s) without a reason
6 | Pages per report >= 1 and at least one target model per pair | PASS | 0 pair(s) to fix
7 | Role mix rows each total 100% | PASS | 0 phase row(s) off
8 | Every plan role has a rate | PASS | 8 of 8 roles priced
9 | Payment milestones total 100% | PASS | 100%
10 | Plan reconciles to estimate within tolerance | PASS | Variance -1.3% (tolerance 5%)
11 | Duration fits the 104-week plan horizon | PASS | 36 weeks
12 | Totals tie: phases = pairs + shared | PASS | Phases 14,325 h vs pairs 14,325 h
13 | Totals tie: role hours = phase hours | PASS | Roles 14,325 h
14 | Totals tie: cost by phase = cost by role (role-mix mode) | PASS | Phase cost $900,381
15 | No error values in calculation tabs | PASS | 0 error cell(s)
| Failed checks | 0

## Scenarios
Scenarios
Compare options: copy the Current column and Paste Special > Values into Scenario A, B or C, then change inputs.
| Measure | Current | Scenario A | Scenario B | Scenario C
| Scenario name | Current
| Fixed price (USD) | 1069220.9198
| Total hours | 17010.7631
| Base hours | 14324.6029
| Duration (weeks) | 36
| Development iterations | 10
| Peak team (FTE) | 18.5
| Average team (FTE) | 9.8194
| Report automation | 0%
| Contingency % | 18.12%
| Cost mode | Role mix

## ChangeLog
Change log
Record every change to inputs, baseline values or formulas.
Version | Date | Author | Change
v2.0 | 2026-10-13 | BI Estimator build | First release of v2, built from the approved requirements document.