## Estimate
BI Migration - Pre-sales Ballpark Estimate
Fill the yellow cells. Results update instantly. For a quotable fixed price use the full v2 estimator.
1. Project settings |  |  |  |  | Results
Client | Example Client |  |  |  | Expected price |  |  | 496450.4
Opportunity | BI modernisation |  |  |  | Ballpark range |  |  | $446,805 to $620,563
Planned start date (Monday) | 2027-01-04 |  |  |  | Total effort (hours) |  |  | 6760
Sprint length (weeks) | 2 |  |  |  | Duration (weeks) |  |  | 27
Development team (engineers) | 6 |  |  |  | Sprints |  |  | 8 x 2-week
Assessment team (FTE) | 2 |  |  |  | Peak team (FTE) |  |  | 9
Automation % (LeapLogic / accelerators) | 0% |  |  |  | Average team (FTE) |  |  | 6.2593
Contingency % | 15% |  |  |  | Blended rate (USD/h) |  |  | 63.8604
Include project manager? | Yes |  |  |  | Planned end date |  |  | 2027-07-09
Include AI readiness? | No |  |  |  | Status |  |  | OK - all checks pass
Hypercare weeks after go-live | 2
2. Scope - one row per source -> target pair (most deals need one row) | [15 empty] | Workings (expand the + above column R to see)
Source BI tool | Target BI tool | Data platform changing? | Reports | Avg pages per report | Complexity profile | % Simple | % Medium | % Complex | % Very complex | % retired / duplicates | Semantic models (target) | Model complexity | Pair factor | Report hours | Model hours | Active | Mix S | Mix M | Mix C | Mix VC | Src archetype | Tgt archetype | Approach share | Inventory pages | Pages to build | Analysis h | Mix flag | Platform change
OBIEE | Power BI | Yes | 300 | 2 | Balanced |  |  |  |  | 20% | 6 | Medium | 1 | 2728.53 | 828 | 1 | 40% | 40% | 15% | 5% | Enterprise semantic-layer | Modern visual / self-service | 100% | 600 | 480 | 176 | 0 | 1
[13 empty] | 0 | 0 | 0 | 0 | 40% | 40% | 15% | 5% | Unmapped | Unmapped | 100% | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 40% | 40% | 15% | 5% | Unmapped | Unmapped | 100% | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 40% | 40% | 15% | 5% | Unmapped | Unmapped | 100% | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 40% | 40% | 15% | 5% | Unmapped | Unmapped | 100% | 0 | 0 | 0 | 0 | 0
% columns are used only when the profile is Custom. A new BI tool must be added on Reference with its archetype.
[12 empty] | Total |  | 2728.53 | 828
3. Effort and cost by phase
Phase | Start week | Weeks | Avg FTE | Hours | Cost (USD) | Basis
Plan (assessment & design) | 1 | 5 | 2 | 400 | 28000 | Initiation + analysis (interpolated) + architecture
Data model & report dev | 6 | 16 | 6 | 3840 | 227328 | Models + reports + security/handover, paced in sprints
Testing & validation (SIT) | 8 | 16 | 1 | 640 | 36800 | One sprint behind development
UAT support | 10 | 16 | 0.5 | 320 | 20608 | Two sprints behind; 1-2 engineers by volume
Prod deployment | 10 | 16 | 0.5 | 320 | 19840 | Deployment support each sprint
Hypercare / parallel run | 26 | 2 | 2 | 160 | 10560 | After final go-live
Project management | 1 | 27 | 1 | 1080 | 88560 | Whole duration
Total (from phases) |  |  |  | 6760 | 431696
Team cost (from Plan grid) |  |  |  |  | 431696
Contingency |  |  |  |  | 64754.4
EXPECTED PRICE |  |  |  |  | 496450.4
Phase workings
4. Checks | [15 empty] | ActivePairs | 1
At least one scope row filled in |  |  |  |  | PASS | [10 empty] | InvPages | 600
Mixes total 100% and every BI tool is known |  |  |  |  | PASS | [10 empty] | PagesBuilt | 480
Role mix rows total 100% (Reference) |  |  |  |  | PASS | [10 empty] | Models | 6
Duration fits the 52-week plan |  |  |  |  | PASS | [10 empty] | TargetTools | 1
Plan grid matches the phase estimate (within 5%) |  |  |  |  | PASS | [10 empty] | AssessHrs | 368
[16 empty] | DevHrs | 3644.53
[16 empty] | PlanWeeks | 5
[16 empty] | Sprints | 8
[16 empty] | DevWeeks | 16
[16 empty] | DevStart | 6
[16 empty] | PagesPerSprint | 60
[16 empty] | UATEnd | 25
[16 empty] | DurWeeks | 27
[16 empty] | CheckFails | 0
Note on C8: 1 or 2 weeks. SIT and UAT follow each sprint.
Note on C9: Engineers building models and reports at peak.
Note on C11: Applied to every phase, capped per phase on Reference.
Note on C14: Copilot / Q&A / Amazon Q / Gemini readiness per semantic model.

## Plan
Delivery plan - Example Client
Phase bars show FTE per week. Team rows are pre-filled from the phases - overwrite any yellow cell to hand-plan; cost follows the grid.
Sprint |  | S1 |  | S2 |  | S3 |  | S4 |  | S5 |  | S6 |  | S7 |  | S8 |  | S9 |  | S10 |  | S11 |  | S12 |  | S13 |  | S14
Week |  | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32 | Wk33 | Wk34 | Wk35 | Wk36 | Wk37 | Wk38 | Wk39 | Wk40 | Wk41 | Wk42 | Wk43 | Wk44 | Wk45 | Wk46 | Wk47 | Wk48 | Wk49 | Wk50 | Wk51 | Wk52
Week starting | time axis 2027-01-04 to 2027-12-27
Phases (FTE per week)
Plan (assessment & design) |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 400
Data model & report dev |  | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 3840
Testing & validation (SIT) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 640
UAT support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 320
Prod deployment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 320
Hypercare / parallel run |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 160
Project management |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1080
Total FTE |  | 3 | 3 | 3 | 3 | 3 | 7 | 7 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 3 | 3 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team | Rate (USD/h) | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32 | Wk33 | Wk34 | Wk35 | Wk36 | Wk37 | Wk38 | Wk39 | Wk40 | Wk41 | Wk42 | Wk43 | Wk44 | Wk45 | Wk46 | Wk47 | Wk48 | Wk49 | Wk50 | Wk51 | Wk52 | Person-weeks | Hours | Cost (USD)
BI Architect | 70 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.6 | 584 | 40880
Lead BI Engineer | 70 | 1 | 1 | 1 | 1 | 1 | 0.9 | 0.9 | 0.9 | 0.9 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 0.15 | 0.15 | 0.15 | 0.15 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.8 | 952 | 66640
Sr BI Engineer | 62 | 0 | 0 | 0 | 0 | 0 | 2.1 | 2.1 | 2.1 | 2.1 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 0.85 | 0.85 | 0.85 | 0.85 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.2 | 1968 | 122016
BI Engineer | 50 | 0 | 0 | 0 | 0 | 0 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.4 | 1536 | 76800
QA Engineer | 57.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 640 | 36800
PM | 82 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1080 | 88560
Total team |  | 3 | 3 | 3 | 3 | 3 | 7 | 7 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 3 | 3 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 6760 | 431696
Hrs per week | 40
Peak team (FTE) | 9
Average team (FTE) | 6.2593
Blended rate (USD/h) | 63.8604
Plan hours vs phase estimate | 0%
Note on B18: Priced as Architect II ¦ G11 ¦ India from the Reference rate card. Overwrite to use another rate.
Note on B19: Priced as Lead II ¦ G11 ¦ India from the Reference rate card. Overwrite to use another rate.
Note on B20: Priced as Sr. Engineer II ¦ G10 ¦ India from the Reference rate card. Overwrite to use another rate.
Note on B21: Priced as Engineer II ¦ G8 ¦ India from the Reference rate card. Overwrite to use another rate.
Note on B22: Priced as Sr. Engineer I ¦ G9 ¦ India from the Reference rate card. Overwrite to use another rate.
Note on B23: Priced as MSE I ¦ G12 ¦ India from the Reference rate card. Overwrite to use another rate.

## Reference
Reference
Numbers behind the ballpark. Same baseline as the full v2 estimator. Change only with BI-team sign-off.
[8 empty] | BI tools |  |  |  | Known pair factors
General | [7 empty] | BI tool | Archetype |  |  | Source | Target | Factor | Key | YesNo | SprintLens
Productive hours per person-week | 40 | [6 empty] | SAP BusinessObjects | Enterprise semantic-layer |  |  | OBIEE | Power BI | 1 | OBIEE¦Power BI | Yes | 1
Ballpark range - low side | -10% | [6 empty] | OBIEE | Enterprise semantic-layer |  |  | Cognos | Power BI | 1.1 | Cognos¦Power BI | No | 2
Ballpark range - high side | 25% | [6 empty] | Oracle Analytics Server | Enterprise semantic-layer |  |  | SAP BusinessObjects | Power BI | 1.25 | SAP BusinessObjects¦Power BI
[8 empty] | MicroStrategy | Enterprise semantic-layer |  |  | Tableau | Power BI | 0.95 | Tableau¦Power BI
Report effort (hours per page) | [7 empty] | Cognos | Enterprise semantic-layer |  |  | SSRS | Power BI | 1.05 | SSRS¦Power BI
Complexity profile | % Simple | % Medium | % Complex | % Very complex |  |  |  | SSRS | Paginated / pixel-perfect |  |  | OBIEE | QuickSight | 1.2 | OBIEE¦QuickSight
Hours per report page | 3.625 | 6.625 | 9.125 | 12.625 |  |  |  | Crystal Reports | Paginated / pixel-perfect |  |  | Cognos | QuickSight | 1.25 | Cognos¦QuickSight
Mostly simple | 60% | 30% | 10% | 0% |  |  |  | Tableau | Modern visual / self-service |  |  | Tableau | QuickSight | 1.1 | Tableau¦QuickSight
Balanced | 40% | 40% | 15% | 5% |  |  |  | Power BI | Modern visual / self-service |  |  | SSRS | QuickSight | 1.2 | SSRS¦QuickSight
Mostly complex | 20% | 40% | 30% | 10% |  |  |  | QuickSight | Modern visual / self-service |  |  | SAP BusinessObjects | QuickSight | 1.3 | SAP BusinessObjects¦QuickSight
Custom | enter on Estimate | enter on Estimate | enter on Estimate | enter on Estimate |  |  |  | Qlik Sense | Modern visual / self-service |  |  | Cognos | Looker | 1.25 | Cognos¦Looker
Average learning gain (0/10/15/20% by quarter of sprints) | 11.25% | [6 empty] | QlikView | Modern visual / self-service |  |  | OBIEE | Looker | 1.2 | OBIEE¦Looker
Data platform change uplift - reports | 5% | [6 empty] | Looker Studio | Modern visual / self-service |  |  | Tableau | Looker | 1.1 | Tableau¦Looker
Data platform change uplift - semantic models | 15% | [6 empty] | Looker | Modern code-based semantic |  |  | SSRS | Looker | 1.2 | SSRS¦Looker
[12 empty] | SAP BusinessObjects | Looker | 1.3 | SAP BusinessObjects¦Looker
Semantic models (hours per target model)
Model complexity | Simple | Medium | Complex | Very complex
Build hours per model | 80 | 120 | 200 | 320
Level names | Simple | Medium | Complex | Very complex
AI readiness hours per model (when included) | 16
Security, ops & handover - hours per pair | 40
Security, ops & handover - hours per model | 8
Assessment and architecture
Anchor (inventory pages) | Pages | Initiation h | Analysis h
Anchor 1 | 100 | 40 | 80
Anchor 2 | 500 | 60 | 160
Anchor 3 | 1000 | 80 | 240
Anchor 4 | 5000 | 120 | 360
Anchor 5 | 10000 | 160 | 480
Assessment hours per semantic model | 4
Architecture hours per target BI tool | 80
Architecture hours per pair | 24 | [6 empty] | Pair factor fallback (source row x target column)
[8 empty] | Source \ Target | Enterprise semantic-layer | Paginated / pixel-perfect | Modern visual / self-service | Modern code-based semantic
Automation caps (share of a phase automation can remove) | [7 empty] | Enterprise semantic-layer | 1.1 | 1 | 1.1 | 1.2
Cap - Assessment | 60% | [6 empty] | Paginated / pixel-perfect | 1 | 0.9 | 1.05 | 1.2
Cap - Semantic model | 40% | [6 empty] | Modern visual / self-service | 1.1 | 1 | 0.95 | 1.1
Cap - Report development | 60% | [6 empty] | Modern code-based semantic | 1 | 1 | 1 | 1
Cap - SIT | 30%
Cap - UAT support | 20%
Cap - Deployment | 60% | [6 empty] | Semantic-model approach share (source row x target column)
[8 empty] | Source \ Target | Enterprise semantic-layer | Paginated / pixel-perfect | Modern visual / self-service | Modern code-based semantic
Testing, UAT, deployment, hypercare (per sprint) | [7 empty] | Enterprise semantic-layer | 100% | 100% | 100% | 100%
SIT crew sizing (% of dev hours) | 15% | [6 empty] | Paginated / pixel-perfect | 30% | 30% | 30% | 100%
UAT support engineers when pages per sprint <= threshold | 1 | [6 empty] | Modern visual / self-service | 100% | 30% | 40% | 100%
UAT support engineers above threshold | 2 | [6 empty] | Modern code-based semantic | 40% | 30% | 40% | 40%
Volume threshold (report pages per sprint) | 150 | [6 empty] | 100% = redesign / author LookML; 40% = translate dataset; 30% = shared datasets for paginated reports.
UAT support weeks per sprint | 1
Deployment engineers | 1
Deployment weeks per sprint | 1
Hypercare crew (FTE) | 2 | [6 empty] | Rate card (bill rates, USD/h)
[8 empty] | Role | Grade ¦ Location | Rate | Key
[8 empty] | MSE II | G13 ¦ India | 87 | MSE II ¦ G13 ¦ India
Role mix by phase (each row totals 100%) | [7 empty] | MSE I | G12 ¦ India | 82 | MSE I ¦ G12 ¦ India
Phase | BI Architect | Lead BI Engineer | Sr BI Engineer | BI Engineer | QA Engineer | PM | Total | Architect II | G12 ¦ India | 70 | Architect II ¦ G12 ¦ India
Plan (assessment & design) | 50% | 50% | 0% | 0% | 0% | 0% | 100% | Architect I | G11 ¦ India | 65 | Architect I ¦ G11 ¦ India
Data model & report dev | 10% | 15% | 35% | 40% | 0% | 0% | 100% | Lead II | G11 ¦ India | 70 | Lead II ¦ G11 ¦ India
Testing & validation (SIT) | 0% | 0% | 0% | 0% | 100% | 0% | 100% | Lead II | G10 ¦ India | 70 | Lead II ¦ G10 ¦ India
UAT support | 0% | 30% | 70% | 0% | 0% | 0% | 100% | Lead I | G10 ¦ India | 62 | Lead I ¦ G10 ¦ India
Prod deployment | 0% | 0% | 100% | 0% | 0% | 0% | 100% | Lead I | G9 ¦ India | 62 | Lead I ¦ G9 ¦ India
Hypercare / parallel run | 0% | 50% | 50% | 0% | 0% | 0% | 100% | Sr. Engineer II | G10 ¦ India | 62 | Sr. Engineer II ¦ G10 ¦ India
Project management | 0% | 0% | 0% | 0% | 0% | 100% | 100% | Sr. Engineer II | G9 ¦ India | 62 | Sr. Engineer II ¦ G9 ¦ India
[8 empty] | Sr. Engineer I | G9 ¦ India | 57.5 | Sr. Engineer I ¦ G9 ¦ India
[8 empty] | Sr. Engineer I | G8 ¦ India | 57.5 | Sr. Engineer I ¦ G8 ¦ India
[8 empty] | Engineer II | G8 ¦ India | 50 | Engineer II ¦ G8 ¦ India
[8 empty] | Engineer II | G6 ¦ India | 50 | Engineer II ¦ G6 ¦ India
[8 empty] | Engineer I | G6 ¦ India | 42 | Engineer I ¦ G6 ¦ India
[8 empty] | Engineer I | G4 ¦ India | 42 | Engineer I ¦ G4 ¦ India
[8 empty] | Jr. Engineer | G4 ¦ India | 35 | Jr. Engineer ¦ G4 ¦ India
[8 empty] | Architect II | G11 ¦ India | 70 | Architect II ¦ G11 ¦ India
[8 empty] | Sr. Architect I | G13 ¦ India | 87 | Sr. Architect I ¦ G13 ¦ India
[8 empty] | Sr. Architect II | G14 ¦ India | 105 | Sr. Architect II ¦ G14 ¦ India
[8 empty] | Sr. Architect II | G13 ¦ India | 105 | Sr. Architect II ¦ G13 ¦ India
[8 empty] | Architect II | G12 ¦ USA | 185 | Architect II ¦ G12 ¦ USA
[8 empty] | MSE I | G12 ¦ USA | 190 | MSE I ¦ G12 ¦ USA
[8 empty] | MSE II | G13 ¦ USA | 210 | MSE II ¦ G13 ¦ USA
Note on B7: Expected price x (1 + this)
Note on B8: Expected price x (1 + this)
Note on B18: Custom SQL re-pointing; ~25% uplift on ~20% of reports